## Tasks and Timeline
| Task | Notes | Start Date | Due Date | Duration (Days) | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 | [5 empty] | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | S | M | T | W | R | F | M | T | W | R | F
1 | Project Initiation
1.1 | Research online and real time food ordering systems |  |  |  | 7 | Peta | bar: WEEK 1 M to WEEK 2 F
1.2 | Gather historical data on ordering for both online and offline process |  |  |  | 1 | Peta | bar: WEEK 1 R
1.3 | Calculate projections and enhancements |  |  |  | 2 | Peta | bar: WEEK 1 R to WEEK 2 F
1.4 | Align and evaluate stakeholders |  |  |  | 2 | Peta | bar: WEEK 1 F to WEEK 2 F
1.5 | Interview members of the staff |  |  |  | 1 | Deanna
1.6 | Create project charter (scope and goals) |  |  |  | 4 | Peta
1.7 | Schedule kick off meeting |  |  |  | 0 | Peta
2 | Sourcing
2.1 | Research table top tablet options and compatibility with the existing POS |  |  |  | 3 | Seydou | bar: WEEK 2 M to WEEK 3 M
2.2 | Identify the number of tablets that needs to be installed |  |  |  | 1 | Alex, Gilly
2.3 | Research data on previous reservation system options |  |  |  | 4 | Peta | bar: WEEK 2 M to WEEK 3 T
2.4 | Procure reliable vendor for sourcing the table top tablets |  |  |  | 2 | Seydou | bar: WEEK 3 T to WEEK 3 W
2.5 | Get quotes and review the costs from the tablets vendor |  |  |  | 3 | Peta, Deanna & Seydou | bar: WEEK 3 R to WEEK 4 M
2.6 | Choose a tablet system from the selected vendor |  |  |  | 2 | Seydou | bar: WEEK 4 T to WEEK 4 W
2.7 | Get vendor timeline and deliverables schedule to meet project goals before deadline |  |  |  | 4 | Peta & Seydou | bar: WEEK 4 W to WEEK 5 F
3 | Planning
3.1 | Create contracts and statement of work for vendors |  |  |  | 3 | Peta, Deanna
3.2 | Message about latest devlopments and launch date to stakeholders |  |  |  | 0 | Peta
3.3 | Promotion for the launch of new services |  |  |  | 14 | Deanna, Seydou & Marketing Team | bar: WEEK 5 M to WEEK 8 F
3.4 | Update marketing/social media plan/calendar |  |  |  | 10 | Peta | bar: WEEK 5 M to WEEK 7 R
3.5 | Project Plan Updates |  |  |  | 13 | Peta | bar: WEEK 5 M to WEEK 8 F
3.6 | Shipping of the table top tablets | Seydou indicates that a shipping delay of 2-3 days is unlikely, but possible, so it could affect this time estimate. Additionally, Terrific Tablets occasionally ships broken devices, which could affect this time estimate. |  |  | 10 | Seydou | bar: WEEK 5 M to WEEK 8 F
3.6 | Installation of the table top tablets |  |  |  | 20 | Peta & Seydou | bar: WEEK 6 W to WEEK 10 T
3.7 | Add featured menu items and coupon values to tablets | Still waiting on Carter for the finalized menu and coupon value mock-ups for upload (aiming for one week but could extend to two). Once mock-ups are received, 3-4 hours to upload |  |  | 0 | Carter & Seydou | bar: WEEK 9 F
3.8 | Update marketing/social media plan/calendar |  |  |  | 10 | Peta | bar: WEEK 8 W to WEEK 10 T
4 | Training
4.1 | Map out seating chart/upload into software |  |  |  | 2 | Seydou | bar: WEEK 10 T to WEEK 10 W
4.2 | Train GMs on new software |  |  |  | 0 | Seydou | bar: WEEK 10 W
4.3 | Train restaurant staff on new software |  |  |  | 2 | Alex, Gilly & Seydou | bar: WEEK 10 R to WEEK 10 F
4.4 | Test run the ordering system |  |  |  | 1 | Seydou | bar: WEEK 11 S
4.5 | Create troubleshoot/support plan for future reference |  |  |  | 4 | Seydou | bar: WEEK 11 M to WEEK 11 R
4.6 | Create launch day plan: staffing, troubleshooting, etc. |  |  |  | 7 | Peta, Deanna & Seydou | bar: WEEK 10 F; WEEK 11 M to WEEK 12 M
5 | Launch
5.1 | Schedule a launch day |  |  |  | 2 | Peta | bar: WEEK 12 T to WEEK 12 W
5.2 | Meeting with stakeholders for alignment on the launch date |  |  |  | 1 | Peta | bar: WEEK 12 R
5.3 | Launch Day |  |  |  | 0 | Peta | bar: WEEK 12 F

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Confidence Rating (H/M/L) | Known Dates
Milestone: Research on online and real time food ordering systems
Research data points on online and real time food ordering systems |  | 3 | H
Gather historical data on ordering for both online and offline process |  | 2 | H
Milestone: Identify the number of tablets that needs to be installed
Work with Gilly (General Manager, North) to identify the number of tablets that needs to be installed in their bar area |  | 1 | H
Work with Alex (General Manager, Downtown) to identify the number of tablets that needs to be installed in their bar area |  | 1 | H
Milestone: Procure reliable vendor for sourcing the table top tablets
Connect marketing team with Terrific Tablets for branding and digital menu design |  |  | M
Choose tablet options and specifications for easy day-to-day use.
Interview with restaurant managers to verify if we will need backup tablets in case of any technical issue |  |  | M
Milestone: Create contracts and statement of work for vendors
Write down the specific obligation of each party, with details around the goods, the service, or the license |  | 1
Outline all legal documents |  | 0
Write down all Payment terms with the vendor |  | 1
Address the consequences if the terms are violated or products not delivered within agreed upon time |  | 1 | H
Milestone: Promotion for the launch of new services
Meeting with marketing & sales team for promotion of new tabletop tablets and a overall digital menu design for tablets |  | 2
Schedule a meeting with Seydou ,Terrific Tabletls and your marketing department to update the menu interface to match the branding and layout of your menus and possibly choose one of those packages |  | 4
Hire website developer and designer for the new website launch |  | 1
Work with marketing & sales team, the developer and the designer for the redesign of the website and any potential social media ads for future promotions |  | 5
Meeting with Carter and Deanna for any possible menu update and get his feedback on the current menu that will be displayed on the tablets and verify any possible changes with Deanna |  | 2
Milestone: Installation of the table top tablets
Work with Seydou with installations of the Terrific Tablets and ensure all the standard features are available on all current tablet models |  | 1
Gather historical data on POS system performance |  | 1
Analyze & summarize POS system performance |  | 0
Research on software requirement |  | 1
Hire software engineer/developer |  | 1
Work with Seydou and the software engineer/developer to make sure the new installed software in the Teriffic Tablets are working and compatible with the current POS system and configure them properly to make the integration as seamless as possible |  | 6 | M
Book electrician for wiring of all the tables in North and Downtown locations where the tablets will be installed for charging the tablets | Electrician is confident they can wire both locations in two business days (16 hours), but since we can’t close the restaurants for a full day we need to schedule two half-days at each location. Notify GMs when their locations need to close for wiring | 4 | H
Software installation process | Possible need to upgrade the POS system to latest version if S&S is running an older version | 4 | L
Work with Seydou to integrate a strong payment gateway, so the customer pays online. |  | 1
Make sure the tablets are securely placed on the tables. |  | 1
Milestone: Train GMs
Train north restaurant GM on the new software | Seydou will train managers first (2 hours), then managers will train all the staff at each location (2 hours for each training plus one hour before and after each training for facilitator prep/debrief) | 0 | H
Train downtown restaurant GM on new software |  | 0 | H
Milestone: Train restaurant staff
Pre-training meeting to introduce tablets and changes to staff before training them on the tablets | (1 hour at each location) | 0
Train north restaurant staff on new software | Managers will train all the staff at each location (2 hours for each training plus one hour before and after each training for facilitator prep/debrief). Gilly and Alex will coordinate with Peta to schedule staff trainings at each of their locations. Each part of the training (pre-training, manager training, staff training) will take place on different days. | 1 | M
Train downtown restaurant staff on new software |  | 1 | M
Meeting with GMs and Seydou to address any issue/concers that might come up during training |  |  | H
Milestone: Test run the ordering system |  | 1
Test run with staff family and friends in order to mimic full service | Gilly recommends testing out the tablets with friends and family to see if everything runs as they should and ro address if any problem arises. |  | M
Collect feedback from test run and address any issue/concern that might have occured during the test run
Look over and implement any necessary feedback from test run

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators
Tablet Functionality | A good average ticket time between placing an order and delivering it to the table is eight minutes for appetizers and 12-15 minutes for entrees. This would help with our goal of bringing down the average table turn time by 30 minutes. | Are the tablets helping to improve the flow of ticket orders? | For appetizers average ticket time should be 8mins or less and for entrees 12-15 mins
To what extent do tablets improve the staff's work performance?
Tablet Functionality | Checkout time of one minute or less | Are the tablets being used by the customers to check out? | Checkout time for any order should be of one minute or less
Are customers having a better dining experience with the tablets?
How quickly are customers learning to navigate the tablets?
|  | Does the customers think the tablets are safe to use in day-to-day hassel-free ordering? | Guests redeem coupons 25% more often
Ease-of-use | Less than 5% of customers who use the tablets to report technical issues each week | Do all the tablets work as expected? | 5% or less customer should report any technical issue each week
Is there any technical glitches/ problems that may increase our goal of less than 5% report of technical issue?
How quickly are customers learning how to navigate the tablets?
|  | Does the Waitstaff can log into their tablet accounts on the first try? | Tablet error logs report a maximum of one error per shift
Customer Satisfaction | Aim for 98% order accuracy by cutting down on incorrect orders | How the guests using the tablets to confirm what they order before sending the ticket to the kitchen? | 98% of orders should be received accurately by using the tablets
Are customers receiving the correct orders?
Guests who use the tablets are 50% more likely to recommend the restaurant to a friend
Customer Satisfaction | Average wait time of ten minutes or less before customers are seated | Does the expected wait times gone down as table turn time decreased? | Customers in-queue wait time should be ten minutes or less
Guests with shorter wait times report wanting to return 20% more often than those with longer wait times
Guests redeem coupons 25% more often
Customer Experience | 80% email capture and restaurant newsletter opt-in | Are the customers happy with the services provided, so that they might want to opt-in for newsletter and future updates? | Atleast 80% of customers chooses to opt-in to the restaurants newsletter
Which customers are posting about their experiences on social media?

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Tablet Functionality | Are the tablets helping to improve the flow of ticket orders? | For appetizers average ticket time should be 8mins or less and for entrees 12-15 mins | On average, how long did it take to receive your food order? | Multiple choice | 0-20 min. | 21-30 min. | 31-40 min. | 41-50 min. | 50+ min.
To what extent do tablets improve the staff's work performance?
Tablet Functionality | Are the tablets being used by the customers to check out? | Checkout time of one minute or less | How would you respond to the following sentence: “I found the checkout process quick, easy, and secure.” | True/False | TRUE | FALSE
| Are customers having a better dining experience with the tablets? |  | On a scale of 1-5, please rate your experience with the tablet overall. | Scaled | 1 | 2 | 3 | 4 | 5
| How quickly are customers learning to navigate the tablets? |  | On a scale of 1-5, how easy was it to use the tablet navigation? | Scaled | 1 | 2 | 3 | 4 | 5
| Does the customers think the tablets are safe to use in day-to-day hassel-free ordering? |  | How confident are you in submitting your payment through a tablet? | Multiple choice | Not at all | Somewhat | Neutral | Confident | Very confident
Ease-of-use | Do all the tablets work as expected? | 5% or less customer should report any technical issue each week | Did you have any technical issues with your tablet? | Yes/No | Yes | No
Is there any technical glitches/ problems that may increase our goal of less than 5% report of technical issue?
| How quickly are customers learning how to navigate the tablets? |  | How well did your waiter instruct you how to use the tablet? | Multiple choice | Not well | OK | Very well
| Does the Waitstaff can log into their tablet accounts on the first try? | Tablet error logs report a maximum of one error per shift | Are there any errors occuring during login at first try? | Yes/No | Yes | No
Customer Satisfaction | How the guests using the tablets to confirm what they order before sending the ticket to the kitchen? | 98% of orders should be received accurately by using the tablets | During your visit, what did you order? Choose all that apply. | Multiple choice | Drinks | Appetizers | Dinner | Dessert
| Are customers receiving the correct orders? |  | Did you use the tablet to put in multiple orders while you were dining? | Yes/No | Yes | No
|  |  | How easy was it to order directly from the menu on the tablet? | Multiple choice | Difficult | Slightly difficult | Neutral | Fairly easy | Very easy
|  |  | Did the kitchen prepare your order correctly? | Yes/No | Yes | No
Customer Satisfaction | Does the expected wait times gone down as table turn time decreased? | Average wait time of ten minutes or less before customers are seated | On average, how long did you wait for your table? | Multiple choice | 0-5 min. | 6-10 min. | 11-15 min. | 15+ min.
Customer Experience | Are the customers happy with the services provided, so that they might want to opt-in for newsletter and future updates? | Atleast 80% of customers chooses to opt-in to the restaurants newsletter | On a scale of 1-5, please rate your experience with the tablet overall. | Scaled | 1 | 2 | 3 | 4 | 5
| Which customers are posting about their experiences on social media? |  | Did you sign up for the newsletter on the tablet? | Yes/No | Yes | No
|  |  | Did you sign up for the Birthday Club? | Yes/No | Yes | No
|  |  | How would you rate this experience vs. a traditional experience with a waiter? | Multiple choice | I liked the tablet experience better, and want to use it exclusively going forward.. | I would like a mix of tablet ordering and waiter interaction. | I disliked the tablets, and would rather have a waiter. | I don’t have a preference.
|  |  | Please tell us anything else about your experience with our new tablet ordering system | Open-ended